## Network Go Backs
Tracking # | CTI Asset # | Store# | Store address | City | State | Zip | Sprint Asset | Delivery date to store | 100% Complete (connected/confirmed) | Confirmed/Delivered not connected | Connected, location not confirmed (no call) | Shipped, not yet delivered to store/installed | Go back with Royal for network/missed rollout/damaged
3149432 | A5001 | 6180 4th Flr | 6160 SPRINT PKWY | OVERLAND PARK | KS | 66211 | W17035645 | 2017-05-01
3149427 | A5004 | 401 | 4901 TOWN CENTER DR | LEAWOOD | KS | 66211 | W17035647 | 2017-05-02
3149429 | A5011 | Mock 2nd Flr | 6180 SPRINT PKWY | OVERLAND PARK | KS | 66211 | W17035684 | 2017-05-02
3149430 | A5012 | 6160 | 6160 SPRINT PKWY | OVERLAND PARK | KS | 66211 | W17035661 | 2017-05-02
3150596 | A5002 | 8420 | 4712 BROADWAY ST | KANSAS CITY | MO | 64112 | W17035653 | 2017-05-03
3150604 | A5005 | 440 | 343 NW BARRY RD | KANSAS CITY | MO | 64155 | W17035641 | 2017-05-03
3150893 | A5006 | 6868 | 5390 JOHNSON DR | MISSION | KS | 66205 | W17035643 | 2017-05-04
3150899 | A5046 | 1447 | 8600 WARD PKWY STE 2130 | KANSAS CITY | MO | 64114 | W17035658 | 2017-05-04
3152207 | A5032 | 443 | 2963 HIGHWAY K | O FALLON | MO | 63368 | W17035644 | 2017-05-10
3152164 | A5008 | 6904 | 517 S GAFFEY | SAN PEDRO | CA | 90731 | W17035672 | 2017-05-11
3152165 | A5010 | 7336 | 1015 S MAIN ST STE A | SANTA ANA | CA | 92701 | W17035679 | 2017-05-11
3152199 | A5013 | 8374 | 662 DENNERY RD STE 101 | SAN DIEGO | CA | 92154 | W17035640 | 2017-05-12
3152167 | A5027 | 7504 | 5146 ARLINGTON AVE | RIVERSIDE | CA | 92504 | W17035673 | 2017-05-12
3152208 | A5033 | 2043 | 2101 W BROADWAY STE A | COLUMBIA | MO | 65203 | W17035639 | 2017-05-12
3152205 | A5003 | 8375 | 3251 20TH AVE SPC 147 | SAN FRANCISCO | CA | 94132 | W17035666 | 2017-05-15
3152203 | A5007 | 7569 | 24901 SANTA CLARA ST #5 | HAYWARD | CA | 94544 | W17035670 | 2017-05-15
3152163 | A5009 | 97 | 80 E COLORADO BLVD | PASADENA | CA | 91105 | W17035671 | 2017-05-15
3152196 | A5016 | 721 | 6409 FAYETTEVILLE RD STE 110 | DURHAM | NC | 27713 | W17035669 | 2017-05-15
3152182 | A5019 | 7313 | 1413 W I240 SERVICE RD #A | OKLAHOMA CITY | OK | 73159 | W17035682 | 2017-05-15
3152155 | A5025 | 663 | 2310 BATTLEGROUND AVE | GREENSBORO | NC | 27408 | W17035683 | 2017-05-15
3152158 | A5031 | 877 | 2100 S HOLDEN RD STE 6 | GREENSBORO | NC | 27407 | W17035674 | 2017-05-15
3152179 | A5035 | 2138 | 6434 SW 3RD ST | OKLAHOMA CITY | OK | 73128 | W17035663 | 2017-05-15
3152206 | A5043 | 8388 | 6040 MAIN ST STE 150 | AMERICAN CANYON | CA | 94503 | W17035656 | 2017-05-15
3152153 | A5044 | 1883 | 2004B S PROMENADE BLVD STE 1 | ROGERS | AR | 72758 | W17035657 | 2017-05-15
3152168 | A5047 | 6993 | 6007 NILES ST | BAKERSFIELD | CA | 93306 | W17035668 | 2017-05-15
3152200 | A5049 | 254 | 31000 COURTHOUSE DR | UNION CITY | CA | 94587 | W17035646 | 2017-05-15
3152133 | A5028 | 129 | 3153 BERLIN TPKE | NEWINGTON | CT | 6111 | W17035681 | 2017-05-17
3152148 | A5034 | 459 | 3101 KENNEDY BLVD W STE B | NORTH BERGEN | NJ | 7047 | W17035652 | 2017-05-17
3152151 | A5036 | 629 | 157 MARKET ST | NEWARK | NJ | 7102 | W17035687 | 2017-05-18
3156457 | A5014 | 7510 | 2073 S GAREY AVE SPC A | POMONA | CA | 91766 | W17037215 | 2017-05-24
3156459 | A5040 | 6991 | 1124 MAIN ST | DELANO | CA | 93215 | W17035649 | 2017-05-24
3154968 | A5056 | 6792 | 2625 S LOOP 35 | ALVIN | TX | 77511 | W17037218 | 2017-05-24
3156704 | A5059 | 6738 | 1025 W 7TH ST | AUBURN | IN | 46706 | W17037207 | 2017-05-24
3156449 | A5063 | 7371 | 1638 ASHLAND ST | ASHLAND | OR | 97520 | W17037228 | 2017-05-24
3156452 | A5070 | 6897 | 3422 WILSHIRE BLVD | LOS ANGELES | CA | 90010 | W17037206 | 2017-05-24
3156451 | A5071 | 6871 | 10747 LONG BEACH BLVD #2 | LYNWOOD | CA | 90262 | W17037234 | 2017-05-24
3156686 | A5076 | 6641 | 3953 W BRD ST | COLUMBUS | OH | 43228 | W17037230 | 2017-05-24
3156456 | A5079 | 7507 | 1350 E MAIN ST | BARSTOW | CA | 92311 | W17037189 | 2017-05-24
3156713 | A5081 | 6503 | 1116 US HWY 9 | OLD BRIDGE | NJ | 8857 | W17037204 | 2017-05-24
3156706 | A5082 | 7687 | 9023 NO FLORIDA AVE | TAMPA | FL | 33604 | W17037155 | 2017-05-24
3156703 | A5089 | 7177 | 3600 S CARROLLTON SPC J | NEW ORLEANS | LA | 70118 | W17037213 | 2017-05-24
3156681 | A5090 | 6600 | 1406 A LEXINGTON AVE | MANSFIELD | OH | 44907 | W17037205 | 2017-05-24
3156699 | A5093 | 6963 | 173 GLEN ST | GLEN COVE | NY | 11542 | W17037152 | 2017-05-24
3156833 | A5094 | 7179 | 8309 W JUDGE PEREZ DR | CHALMETTE | LA | 70043 | W17037196 | 2017-05-24
3156689 | A5096 | 6650 | 7940 E BROAD ST | REYNOLDSBURG | OH | 43068 | W17037167 | 2017-05-24
3156698 | A5097 | 6958 | 112A WHEELER RD | CENTRAL ISLIP | NY | 11722 | W17037179 | 2017-05-24
3154998 | A5039 | 6834 | 1734 SW COURT PL | PENDLETON | OR | 97801 | W17035654 | 2017-05-24
3157915 | A5038 | 7785 | 6183 OXON HILL RD | OXON HILL | MD | 20745 | W17035662 | 2017-05-31
3156690 | A5092 | 6652 | 1761 W LANE AVE | UPPER ARLINGTON | OH | 43221 | W17037211 | 2017-05-31
3157944 | A5050 | 7647 | 5777 MANATEE AVE W | BRADENTON | FL | 34209 | W17037177 | 2017-05-31
3157939 | A5105 | 7950 | 282 SOUTH 500 West #B | West BOUNTIFUL | UT | 84010 | W17037183 | 2017-05-31
3156694 | A5037 | 6632 | 1977 S FEDERAL BLVD | DENVER | CO | 80219 | W17035685 | 2017-06-01
3157932 | A5103 | 7834 | 5707 4TH ST STE 2 | LUBBOCK | TX | 79416 | W17037148 | 2017-06-01
3158188 | A5109 | 7153 | 361 Opry Mills Dr | NASHVILLE | TN | 37214 | W17037151 | 2017-06-01
3154974 | A5121 | 6656 | 120 AERENSON DR | MILFORD | DE | 19963 | W17037186 | 2017-06-01
3159363 | A5055 | 6559 | 5316 N MILWAUKEE AVE #8 | CHICAGO | IL | 60630 | W17037201 | 2017-06-07
3160490 | A5139 | 6619 | 6720 CAMBDEN BLVD | FOUNTAIN | CO | 80817 | W17037165 | 2017-06-07
3160486 | A5140 | 6370 | 1891 CHAMBLEE TUCKER RD | CHAMBLEE | GA | 30341 | W17037161 | 2017-06-07
3160503 | A5141 | 7809 | 2700 E 23RD ST. | FREMONT | NE | 68025 | W17037598 | 2017-06-07
3160912 | A5153 | 7432 | 10735 E APACHE TRL STE 103 | APACHE JUNCTION | AZ | 85120 | W17037617 | 2017-06-07
3161497 | A5165 | 7675 | 5016 WELLINGTON AVE | VENTNOR CITY | NJ | 8406 | W17037604 | 2017-06-07
3161503 | A5167 | 7455 | 11630 KELEKET DR. | PITTSBURGH | PA | 15235 | W17037596 | 2017-06-07
3161814 | A5174 | 6612 | 3578 MAYFIELD RD. | CLEVELAND HTS | OH | 44118 | W17037575 | 2017-06-07
3159305 | A5123 | 423 | 8300 Gaylord Pkwy STE 11 | FRISCO | TX | 75034 | W17037156 | 2017-06-08
3152193 | A5021 | 323 | 2226 WALNUT ST | CARY | NC | 27518 | W17035642 | 2017-05-15
3152178 | A5030 | 2136 | 2410 NW CACHE RD STE A | LAWTON | OK | 73505 | W17035678 | 2017-05-15
3152202 | A5042 | 517 | 5194 STEVENS CREEK BLVD | SAN JOSE | CA | 95129 | W17035638 | 2017-05-15
3153916 | A5052 | 1308 | 3535 CLEAR LAKE CITY BLVD STE 100 | HOUSTON | TX | 77059 | W17037219 | 2017-05-15
3153921 | A5051 | 2199 | 2200 E PALM VALLEY BLVD STE 105 | ROUND ROCK | TX | 78665 | W17037202 | 2017-05-17
3153913 | A5000 | 1096 | 2811 Craig Dr Ste 104 | MCKINNEY | TX | 75070 | W17037223 | 2017-05-19
3152143 | A5018 | 1318 | 5040 LEMMON AVE Suite 100 | DALLAS | TX | 75209 | W17035650 | 2017-05-23
3156460 | A5023 | 7852 | 126 SW 148TH ST | BURIEN | WA | 98166 | W17035648 | 2017-05-24
3157909 | A5024 | 6849 | 7706 STATE AVE | KANSAS CITY | KS | 66112 | W17035680 | 2017-05-24
3156458 | A5041 | 6880 | 5804 N FIGUEROA | LOS ANGELES | CA | 90042 | W17035667 | 2017-05-24
3154840 | A5057 | 7617 | 504 BYPASS 72 NW | GREENWOOD | SC | 29649 | W17037214 | 2017-05-24
3156443 | A5060 | 7353 | 1281 N HWY 99W | MCMINNVILLE | OR | 97128 | W17037217 | 2017-05-24
3156455 | A5062 | 6923 | 5160 VINELAND AVE STE 111 | NORTH HOLLYWOOD | CA | 91601 | W17037193 | 2017-05-24
3156705 | A5065 | 6739 | 2013 N MICHIGAN ST | PLYMOUTH | IN | 46563 | W17037222 | 2017-05-24
3156466 | A5074 | 7476 | 355 RESERVOIR AVE | PROVIDENCE | RI | 2907 | W17037199 | 2017-05-24
3156468 | A5077 | 6453 | 1524 DORCHESTER AVE | DORCHESTER | MA | 2122 | W17037192 | 2017-05-24
3156697 | A5080 | 6950 | 1690 SUNRISE HWY | MERRICK | NY | 11566 | W17037216 | 2017-05-24 | store is being remodeled. Royal went to store and verified with pictures. Unable to connect until remodel is completed.
3156462 | A5083 | 7714 | 299 E PLUMB LN STE D | RENO | NV | 89502 | W17037203 | 2017-05-24
3156696 | A5084 | 7285 | 517 RIVER RD | EDGEWATER | NJ | 7020 | W17037225 | 2017-05-24
3156693 | A5085 | 6628 | 12385 W 64TH ST | ARVADA | CO | 80004 | W17037236 | 2017-05-24
3156692 | A5086 | 6625 | 5305 E COLFAX AVE UNIT A | DENVER | CO | 80220 | W17037187 | 2017-05-24
3156463 | A5087 | 7719 | 578 N MCCARRAN BLVD | SPARKS | NV | 89431 | W17037212 | 2017-05-24
3156702 | A5095 | 7234 | 254 7TH AVE | BROOKLYN | NY | 11215 | W17037191 | 2017-05-24
3156710 | A5098 | 7694 | 3850 S DALE MABRY | TAMPA | FL | 33611 | W17037184 | 2017-05-24
3153908 |  | 1304 | 4811 OVERTON RIDGE BLVD STE 236 | FORT WORTH | TX | 76132 |  | 2017-05-24
3154834 | A5073 | 6394 | 5186 KYLE CTR DR STE 9 | KYLE | TX | 78640 | W17037227 | 2017-05-24
3154987 | A5022 | 7097 | 2690 CRANSTON RD | BELOIT | WI | 53511 | W17035659 | 2017-05-24
3154989 | A5066 | 7150 | 4450 HWY 17 S UNIT 1 | MURRELLS INLET | SC | 29576 | W17037195 | 2017-05-24
3152176 | A5020 | 7374 | 2315 S FEDERAL HWY | FORT PIERCE | FL | 34982 | W17035651 | 2017-05-24
3154980 | A5067 | 7404 | 223 SHOEMAKER RD STE 138 | POTTSTOWN | PA | 19464 | W17037198 | 2017-05-24
3154828 | A5054 | 7847 | 1804 E AMARILLO BLVD | AMARILLO | TX | 79107 | W17037235 | 2017-05-24
3157941 | A5100 | 7641 | 8396 N LOCKWOOD RIDGE RD | SARASOTA | FL | 34243 | W17037200 | 2017-05-31
3157937 | A5061 | 7866 | 4217 WHEATON WAY STE N | BREMERTON | WA | 98310 | W17037154 | 2017-05-31
3157912 | A5064 | 6439 | 192 BORDER ST | E BOSTON | MA | 2128 | W17037224 | 2017-05-31
3157945 | A5101 | 7693 | 11685 BOYETTE RD #104 | RIVERVIEW | FL | 33569 | W17037178 | 2017-05-31
3157935 | A5102 | 7842 | 2420 19TH SPC 1 | LUBBOCK | TX | 79401 | W17037173 | 2017-05-31
3157938 | A5104 | 7756 | 1828 W 9000 S | WEST JORDAN | UT | 84088 | W17037182 | 2017-05-31
3157921 | A5107 | 7284 | 100 BROADWAY | ELMWOOD PARK | NJ | 7407 | W17037180 | 2017-05-31
3157924 | A5124 | 6951 | 293 MIDDLE COUNTRY RD | SELDEN | NY | 11784 | W17037170 | 2017-05-31
3157925 | A5126 | 6953 | 2413 JERICHO TNPK | GARDEN CTY PARK | NY | 11040 | W17037171 | 2017-05-31
3157926 | A5127 | 7238 | 1010 FLATBUSH AVE | BROOKLYN | NY | 11226 | W17037172 | 2017-05-31
3154982 |  | 7057 | 35 GOODMAN RD W STE E | SOUTHAVEN | MS | 38671 |  | 2017-05-31
3152177 |  | 7065 | 4640 FOREST HILL BLVD | W PALM BEACH | FL | 33415 |  | 2017-05-31
3155002 |  | 7701 | 3325 SECOR RD STE 3337 | TOLEDO | OH | 43606 |  | 2017-05-31
3155000 |  | 7820 | 1055 W BROADWAY | CentralIA | IL | 62801 |  | 2017-05-31
3154979 |  | 7844 | 3300 W ILLINOIS SPC A | MIDLAND | TX | 79703 |  | 2017-05-31
3157918 | A5099 | 7280 | 711 E 1ST AVE STE 13 | ROSELLE | NJ | 7203 | W17037150 | 2017-06-01
3157929 | A5106 | 7330 | 32161 CAMINO CAPISTRANO | SN JN CPSTRN | CA | 92675 | W17037185 | 2017-06-01
3157928 | A5108 | 6890 | 13209 GLADSTONE | SYLMAR | CA | 91342 | W17037145 | 2017-06-01
3158752 | A5110 | 6912 | 1615 N VERMONT AVE | LOS ANGELES | CA | 90027 | W17037146 | 2017-06-01
3158748 | A5111 | 7506 | 13132 PALM DR | DESERT HOT SPRG | CA | 92240 | W17037147 | 2017-06-01
3158194 | A5115 | 1389 | 1400 West SW Loop 323 Suite 70 | Tyler | TX | 75703 | W17037181 | 2017-06-01
3154993 | A5120 | 7670 | 635 S CLINTON AVE STE 205 | TRENTON | NJ | 8611 | W17037139 | 2017-06-01
3159301 | A5125 | 324 | 20225 Highway 59 North | HUMBLE | TX | 77338 | W17037169 | 2017-06-01
3154967 |  | 6747 | 607 ST JAMES AVE STE A | GOOSE CREEK | SC | 29445 |  | 2017-06-01
3160436 | A5134 | 876 | 4717 SHARON RD STE 2A | CHARLOTTE | NC | 28210 | W17037160 | 2017-06-05
3160520 | A5136 | 911 | 8606 N CHURCH RD | KANSAS CITY | MO | 64157 | W17037158 | 2017-06-05
3159325 | A5112 | 7502 | 2200 W FLORIDA AVE #270 | HEMET | CA | 92545 | W17037174 | 2017-06-07
3159323 | A5113 | 7255 | 2608 S SAVIERS RD | OXNARD | CA | 93033 | W17037176 | 2017-06-07
3159315 | A5117 | 7369 | 919 S W 5TH AVE | PORTLAND | OR | 97204 | W17037144 | 2017-06-07
3159322 | A5118 | 6891 | 11719 ROSECRANS AVE | NORWALK | CA | 90650 | W17037143 | 2017-06-07
3159321 | A5119 | 6881 | 1817 CESAR CHAVEZ AVE | LOS ANGELES | CA | 90033 | W17037175 | 2017-06-07
3159309 | A5122 | 7525 | 709 RIDGE RD E | ROCHESTER | NY | 14621 | W17037137 | 2017-06-07
3159331 | A5128 | 7378 | 600 S HUNT CLUB BLVD | APOPKA | FL | 32703 | W17037141 | 2017-06-07
3159318 | A5132 | 7244 | 140 E LITTLE CREEK RD | NORFOLK | VA | 23505 | W17037140 | 2017-06-07
3160505 | A5133 | 6552 | 1272 N LAKE ST. | AURORA | IL | 60506 | W17037168 | 2017-06-07
3160493 | A5135 | 7288 | 168 MARKET ST. | PATERSON | NJ | 7505 | W17037153 | 2017-06-07
3160495 | A5138 | 6940 | 2342 E BONANZA RD | LAS VEGAS | NV | 89101 | W17037166 | 2017-06-07
3160474 | A5142 | 7562 | 20566 REDWOOD RD | CASTRO VALLEY | CA | 94546 | W17037619 | 2017-06-07
3160477 | A5143 | 7605 | 1419 MAIN ST., BOX 5 | WATSONVILLE | CA | 95076 | W17037579 | 2017-06-07
3160790 | A5146 | 7538 | 513 SWEETWATER RD | SPRING VALLEY | CA | 91977 | W17037597 | 2017-06-07
3160894 | A5150 | 7755 | 4576 S 4000 W | W VALLEY CITY | UT | 84120 | W17037587 | 2017-06-07
3160900 | A5151 | 7642 | 3280 TAMIAMI TRAIL | PORT CHARLOTTE | FL | 33952 | W17037601 | 2017-06-07
3160995 | A5156 | 6952 | 1975 WANTAGH AVE | WANTAGH | NY | 11973 | W17037615 | 2017-06-07
3160991 | A5157 | 6949 | 51 WICKS DR. | BRENTWOOD | NY | 11717 | W17037583 | 2017-06-07
3160885 | A5159 | 7077 | 167 S POMPANO PKWY | POMPANO BEACH | FL | 33069 | W17037581 | 2017-06-07
3161005 | A5160 | 7206 | 22-32 31ST ST. | ASTORIA | NY | 11105 | W17037573 | 2017-06-07
3160882 | A5161 | 7066 | 19831 NW 2ND AVE | MIAMI GARDENS | FL | 33169 | W17037603 | 2017-06-07
3160901 | A5162 | 7646 | 3747 E TAMIAMI TRAIL | NAPLES | FL | 34112 | W17037629 | 2017-06-07
3161500 | A5166 | 7678 | 775 N DELSEA DR. | GLASSBORO | NJ | 8028 | W17037595 | 2017-06-07
3161501 | A5168 | 7442 | 15937 STATE RD. RT 170 | E. LIVERPOOL | OH | 43920 | W17037594 | 2017-06-07
3161802 | A5172 | 6434 | 601 MEMORIAL DR. STE D | CHICOPEE | MA | 1020 | W17037613 | 2017-06-07
3161819 | A5175 | 6644 | 61243 SOUTHGATE PKWY #A4 | CAMBRIDGE | OH | 43725 | W17037605 | 2017-06-07
3161808 | A5178 | 6429 | 94 BOSTON ST. | LYNN | MA | 1904 | W17037263 | 2017-06-07
3161487 | A5147 | 1232 | 9901 77TH ST STE 870 | PLEASANT PRAIRIE | WI | 53158 | W17037618 | 2017-06-08
3160880 | A5148 | 1316 | 2501 W PARMER LN #125A | AUSTIN | TX | 78727 | W17037582 | 2017-06-08
3164578 | A5218 | 6943 | 334 W LAKE MEAD PKWY | HENDERSON | NV | 89015 | W17037291 | 2017-06-14
3159328 | A5130 | 6764 | 823 CALIFORNIA AVE | WAHIAWA | HI | 96786 | W17037163 | 2017-06-14
3160897 | A5149 | 7757 | 1466 N STATE ST | OREM | UT | 84057 | W17037602 | 2017-06-14
3162701 | A5152 | 7143 | 2803 CHURCH ST | CONWAY | SC | 29526 | W17037620 | 2017-06-14
3162738 | A5154 | 6822 | 5828 CRAWFORDSVILLE RD #B | INDIANAPOLIS | IN | 46224 | W17037626 | Wed 6/21 8PM
3160915 | A5155 | 7433 | 4015 N 16TH ST. | PHOENIX | AZ | 85016 | W17037616 | 2017-06-14
3163253 | A5170 | 7560 | 15100 HESPERIAN BLVD #208 | SAN LEANDRO | CA | 94578 | W17037612 | 2017-06-14
3163743 | A5171 | 6831 | 1910 W FRANCIS AVE | SPOKANE | WA | 99205 | W17037607 | 2017-06-14
3162707 | A5259 | 6583 | 4462 MONTGOMERY RD | CINCINNATI | OH | 45212 | W17037505 | 2017-06-14
3162687 | A5177 | 7438 | 961 FREEPORT RD | PITTSBURGH | PA | 15238 | W17037243 | 2017-06-14
3162704 | A5179 | 6534 | 8128 S TRYON ST | CHARLOTTE | NC | 28273 | W17037241 | 2017-06-14
3162688 | A5180 | 7673 | 1500 ROUTE 47 SOUTH | RIO GRANDE | NJ | 8242 | W17037238 | 2017-06-14
3162692 | A5181 | 7152 | 15543 OLD HICKORY BLVD | NASHVILLE | TN | 37211 | W17037614 | 2017-06-14
3162691 | A5183 | 6431 | 233 MEMORIAL AVE | W SPRINGFIELD | MA | 1089 | W17037592 | 2017-06-14
3162677 | A5184 | 7194 | 51 BURNETT BLVD STE #7 | POUGHKEEPSIE | NY | 12603 | W17037623 | 2017-06-14
3162699 | A5185 | 7786 | 1528 BENNING RD NE | WASHINGTON | DC | 20002 | W17037591 | 2017-06-14
3163237 | A5186 | 7225 | 965 RICHMOND AVE STE G | STATEN ISLAND | NY | 10314 | W17037593 | 2017-06-14
3163239 | A5187 | 7287 | 22 LEXINGTON AVE | PASSAIC | NJ | 7055 | W17037289 | 2017-06-14
3163229 | A5189 | 6886 | 11970 GARVEY AVE | EL MONTE | CA | 91732 | W17037281 | 2017-06-14
3163230 | A5190 | 7329 | 1005 N STATE COLLEGE BLVD | ANAHEIM | CA | 92806 | W17037586 | 2017-06-14
3163240 | A5191 | 7530 | 13909 NACOGDOCHES RD #101 | SAN ANTONIO | TX | 78217 | W17037262 | 2017-06-14
3163235 | A5192 | 7643 | 1315 HOMESTEAD RD N STE B | LEHIGH ACRES | FL | 33936 | W17037265 | 2017-06-14
3163250 | A5196 | 293 | 885 N ALAFAYA TRL | ORLANDO | FL | 32828 | W17037576 | 2017-06-14
3163251 | A5197 | 7373 | 7222 W COLONIAL DR | ORLANDO | FL | 32818 | W17037631 | 2017-06-14
3163756 | A5198 | 7717 | 1012 FLORIN RD | SACRAMENTO | CA | 95831 | W17037278 | 2017-06-14
3163236 | A5199 | 7686 | 1291 S MISSOURI AVE | CLEARWATER | FL | 33756 | W17037277 | 2017-06-14
3163739 | A5201 | 6462 | 110 RIVER ST | WALTHAM | MA | 2453 | W17037292 | 2017-06-14
3163754 | A5206 | 7472 | 150 CARR 940 STE 210 | FAJARDO | PR | 738 | W17037287 | 2017-06-14
3163752 | A5203 | 7470 | 350 CARR 3 STE 140 | HUMACAO | PR | 791 | W17037279 | 2017-06-14
3163748 | A5207 | 7803 | 3423 L ST #15 | OMAHA | NE | 68107 | W17037264 | 2017-06-14
3163764 | A5208 | 7087 | 945 E 8TH AVE | HIALEAH | FL | 33010 | W17037248 | 2017-06-14
3163759 | A5209 | 7311 | 11613 E 31 ST | TULSA | OK | 74146 | W17037578 | 2017-06-14
3163751 | A5210 | 6556 | 1030-B SUMMIT ST | ELGIN | IL | 60120 | W17037625 | 2017-06-14
3163742 | A5215 | 6620 | 4090 AUSTIN BLUFFS PKWY | COLORADO SPRINGS | CO | 80918 | W17037589 | 2017-06-14
3164577 | A5220 | 6970 | 1769 GRAND AVE | BALDWIN | NY | 11510 | W17037197 | 2017-06-14
3161812 | A5173 | 6412 | 6815 PEARL RD. | MIDDLEBURG HTS | OH | 44130 | W17037628 | 6/22/2017 @ 8pm
3159333 | A5129 | 7385 | 1455 E SEMORAN BLVD #117 | CASSELBERRY | FL | 32730 | W17037162 | 2017-06-21
3159327 | A5131 | 6758 | 3-2600 KAUMUALII HWY B-8 | LIHUE | HI | 96766 | W17037159 | 2017-06-21
3160481 | A5137 | 7610 | 1990 FREEDOM BLVD | FREEDOM | CA | 95019 | W17037164 | 2017-06-21
3160786 | A5144 | 7542 | 4371 UNIVERSITY AVE # 400 | SAN DIEGO | CA | 92105 | W17037580 | late the week of 6/19
3160893 | A5164 | 7856 | 1541 NW LOUISIANA AVE | CHEHALIS | WA | 98532 | W17037574 | 2017-06-21
3161806 | A5169 | 7271 | 279 COTTAGE GROVE RD. | BLOOMFIELD | CT | 6002 | W17037632 | TBD
3162695 | A5182 | 6474 | 1593 MILITARY RD | NIAGARA FALLS | NY | 14304 | W17037624 | 2017-06-21
3163234 | A5193 | 7563 | 1353 WASHINGTON AVE | SAN LEANDRO | CA | 94577 | W17037274 | 2017-06-21
3163757 | A5200 | 7722 | 1281 W YOSEMITE | MANTECA | CA | 95337 | W17037268 | 2017-06-21
3163788 | A5204 | 8865 | 4848 VAN DORN ST #1 | LINCOLN | NE | 68506 | W17037609 | 2017-06-21
3163746 | A5212 | 7100 | 2500 MILTON AVE | JANESVILLE | WI | 53545 | W17037585 | 6/20/2017 mid day
3164583 | A5214 | 7700 | 3491 THOMASVILLE RD #12 | TALLAHASSEE | FL | 32309 | W17037622 | 2017-06-21
3164581 | A5216 | 7309 | 1640 S SOONER RD #C | MIDWEST CITY | OK | 73110 | W17037584 | 2017-06-21
3164580 | A5217 | 7183 | 303 W ESPLANADE STE D | KENNER | LA | 70065 |  | 2017-06-21
3164579 | A5219 | 7382 | 1421 S BABCOCK ST | MELBOURNE | FL | 32901 | W17037606 | 2017-06-21
3164589 | A5221 | 7696 | 7248 GALL BLVD | ZEPHYRHILLS | FL | 33541 | W17037283 | 2017-06-21
3164575 | A5222 | 6642 | 3547 CLEVELAND AVE | COLUMBUS | OH | 43224 | W17037286 | 2017-06-21
3165672 | A5228 | 6427 | 740 CRESCENT ST | BROCKTON | MA | 2302 | W17037275 | 2017-06-21
3165673 | A5227 | 6430 | 155 CENTRE ST | MALDEN | MA | 2148 | W17037588 | 2017-06-21
3165685 | A5230 | 6584 | 8541 WINTON RD | CINCINNATI | OH | 45231 | W17037266 | 2017-06-21
3165692 | A5224 | 6776 | 14418 BELLAIRE BLVD | HOUSTON | TX | 77083 | W17037572 | 2017-06-21
3165697 | A5234 | 6816 | 3349 KENTUCKY AVE | INDIANAPOLIS | IN | 46221 | W17037462 | 2017-06-21
3165698 | A5232 | 6818 | 135 S CHAUNCEY AVE STE F1 | W LAFAYETTE | IN | 47906 | W17037611 | 2017-06-21
3165668 | A5225 | 7269 | 39 SOUTH MAIN ST | WEST HARTFORD | CT | 6107 | W17037272 | 2017-06-21
3165670 | A5226 | 7659 | 1 PADANARAM RD | DANBURY | CT | 6811 | W17037745 | 2017-06-21
3165688 | A5231 | 7779 | 615 12TH ST NW | WASHINGTON | DC | 20005 | W17037290 | 2017-06-21
3165681 | A5229 | 7968 | 3866 PAXTON RD STE D | CINCINNATI | OH | 45209 | W17037282 | 2017-06-21
3165695 | A5223 | 354 | 10255 North Fwy STE A | HOUSTON | TX | 77037 | W17037271 | 2017-06-22
3164572 | A5211 | 1836 | 2300 HOLCOMB BRIDGE RD STE 402 | ROSWELL | GA | 30076 | W17037269 | 2017-06-26
3163761 | A5188 | 6833 | 131 E BEST AVE | COEUR D ALENE | ID | 83814 | W17037270 | 2017-06-22
3156834 | A5078 | 308 | 1652 S FEDERAL HWY | DELRAY BEACH | FL | 33483 | W17037220 | 2017-06-20
3156835 | A5091 | 316 | 2912 N UNIVERSITY DR STE 14 | CORAL SPRINGS | FL | 33065 | W17037157 | 2017-06-20
3157947 | A5114 | 411 | 1913 PRESTON RD STE 100 | PLANO | TX | 75093 | W17037149 | 2017-06-20
3152145 | A5017 | 426 | 1765 N TOWN EAST BLVD STE 133 AND 135 | MESQUITE | TX | 75150 | W17035676 | 2017-06-20
3152173 | A5048 | 1138 | 2835 BARTLETT BLVD | BARTLETT | TN | 38134 | W17035665 | 2017-06-21
3152175 | A5026 | 1473 | 5299 POPLAR AVE | MEMPHIS | TN | 38119 | W17035655 | 2017-06-21
3152141 | A5015 | 1766 | 5368 HWY 280 | BIRMINGHAM | AL | 35242 | W17035675 | 2017-06-21
3159312 | A5116 | 8840 | 120 HOOSICK ST | TROY | NY | 12180 | W17037142 | 2017-06-20
3161001 | A5163 | 6956 | 353 WILLAIM FLOYD PKWY | SHIRLEY | NY | 11967 | W17037503 | 2017-06-21
3160890 | A5158 | 7875 | 1523 3RD AVE | SEATTLE | WA | 98101 | W17037590 | TBD (short ceiling)
3166303 | A5244 | 6942 | 3531 S RAINBOW BLVD | LAS VEGAS | NV | 89103 | W17037488 | 2017-06-21
3166304 | A5246 | 6882 | 1601 E 103RD ST STE 4 | LOS ANGELES | CA | 90002 | W17037510 | 2017-06-21
3166305 | A5245 | 7494 | 194 W FOOTHILL | RIALTO | CA | 92376 | W17037497 | 2017-06-21
3166306 | A5247 | 6908 | 825 N LAKE AVE | PASADENA | CA | 91104 | W17037502 | 2017-06-21
3166307 | A5235 | 7508 | 1458 E FLORIDA AVE | HEMET | CA | 92544 | W17037483 | 2017-06-21
3166315 | A5238 | 244 | 616 N UIVERSITY DR STE D8 | PEMBROKE PINES | FL | 33024 | W17037489 | 2017-06-19
3166308 | A5237 | 7082 | 10613 BIRD RD | MIAMI | FL | 33165 | W17037487 | 2017-06-21
3166310 | A5205 | 7583 | 43 E 4TH AVE | SAN MATEO | CA | 94401 | W17037610 | 2017-06-22
3166311 | A5236 | 7580 | 673 TRANCAS | NAPA | CA | 94558 | W17037500 | 2017-06-21
3166312 | A5239 | 1310 | 1370 EAST 70TH ST STE 600 | SHREVEPORT | LA | 71105 | W17037486 | 2017-06-22
3166314 | A5243 | 1301 | 2880 Louisville Ave Ste 3 | Monroe | LA | 71201 | W17037485 | 2017-06-16
3166393 | A5240 | 7984 | 12041 W ALAMEDA PKWY | LAKEWOOD | CO | 80228 | W17037508 | 2017-06-21
3166408 | A5242 | 7289 | 489 BRDWAY | BAYONNE | NJ | 7002 | W17037491 | 2017-06-16
S01079730 | A5206 | 7463 | 320 CARR 153 STE 85 | SANTA ISABEL | PR | 757 | W17037577 | 2017-06-22
3156465-2 | A5260 | 7778-2 | 1141 UNIVERSITY BLVD | TAKOMA PARK | MD | 20912 | W17037515 | 2017-07-11
3154986-2 | A5075 | 7767 | 42 GUSABEL AVE | NASHUA | NH | 3063 | W17037498 | 2017-05-24
3163231-2 | A5258 | 7493-2 | 14712 LA PAZ DR #104 | VICTORVILLE | CA | 92392 | W17037496 | 2017-06-26
3163233-2 | A5257 | 7497-2 | 18284 COLLIER AV STE 1200 | LAKE ELSINORE | CA | 92530 | W17037504 | 2017-06-26
3163762-2 | A5250 | 841-2 | 1501b W Bay Area Blvd | WEBSTER | TX | 77598 | W17037514 | 2017-07-19
3168242 | A5255 | 6498 | 2545 E EUCLID AVE | DES MOINES | IA | 50317 | W17037461 | 2017-06-29
3168244 | A5249 | 7185 | 5875 MAIN ST STE D | ZACHARY | LA | 70791 | W17037509 | 2017-07-20
3160038 | A5251 | 6673 | 3901 E BELKNAP | FORT WORTH | TX | 76111 | W17037490 | 2017-06-21
3168247 | A5252 | 6730 | 1745 TROUP HWY | TYLER | TX | 75701 | W17037506 | 2017-06-21
3168250 | A5254 | 7142 | 2518 S BRENTWOOD BLVD | BRENTWOOD | MO | 63144 | W17037484 | 2017-06-21
3162707-2 | A5259 | 6583-2 | 4462 MONTGOMERY RD | CINCINNATI | OH | 45212 | W17037505 | 2017-06-22
3164580-2 | A5256 | 7183-2 | 303 W ESPLANADE STE D | KENNER | LA | 70065 | W17037260 | 2017-06-22
3161495-2 | A5283 | 1239-2 | 2970 N EAGLE ROAD STE 104 | MERIDIAN | ID | 83646 | W17037247 | 2017-07-24
3156703-2 | A5253 | 7177-2 | 3600 S CARROLLTON SPC J | NEW ORLEANS | LA | 70118 | W17037482 | 2017-07-24
3180182 | A5284 | 8386 | 4057 GRAND PKWY STE 200 | SPRING | TX | 77386 | W17037423 | 2017-07-24
3180175 | A5321 | 1307 | 12711 BLANCO RD STE 104 | SAN ANTONIO | TX | 78231 | W17037420 | 2017-07-24
3180180 | A5217 | 1315 | 14237 E SAM HOUSTON PKWY N STE 900 | HOUSTON | TX | 77044 | W17037245 | 2017-07-24
3179387 | A5289 | 7255-2 | 2608 S SAVIERS RD | OXNARD | CA | 93033 | W17037427 | 2017-07-24
3165689-2 | A5320 | 7777-2 | 4135 CHESHIRE STATION PL | WOODBRIDGE | VA | 22193 | W17037426 | 2017-07-24
3179389 | A5280 | 7507-2 | 1350 E MAIN ST | BARSTOW | CA | 92311 | W17037276 | 2017-07-26
3172581 | A5272 | 879 | 6860 Hwy 6 N STE E | HOUSTON | TX | 77084 | W17037257 | 2017-07-06
3172584 | A5271 | 1233 | 6336 W 95TH STREET | OAK LAWN | IL | 60453 | W17037258 | 2017-07-06
3172586-2 | A5275 | 893 | 1440 East Lake Woodlakes Drive Ste E | SPRING | TX | 77380 | W17037250 | 2017-07-10
3166301-2 | A5322 | 7223-2 | 901 AVE OF THE AMERICAS SP 166 | NEW YORK | NY | 10001 | W17037419 | 2017-07-10
3180218 | A5261 | 1236 | 142 WORCHESTER ROAD | FRAMINGHAM | MA | 1702 |  | 2017-07-24
3166299 | A5241 | 6994 | 3402 N BLACKSTONE #180 | FRESNO | CA | 93726 | W17037493 | TBD
| A5306 | 448 | 1010 Town Center Blvd | WESLACO | TX | 78596 | W17037466 | 2017-08-03
| A5020 | unknown
| A5045 | unknown
| A5053 | unknown
| A5068 | unknown
| A5072 | unknown
go backs
3175891 | A5331 | 543 | 320 GELLERT BLVD | DALY CITY | CA | 94015 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175895 | A5332 | 1841 | 3020 EL CERRITO PLAZA | EL CERRITO | CA | 94530 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175898 | A5328 | 1860 | 690 MARKET ST | SAN FRANCISCO | CA | 94104 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175899 | A5327 | 2009 | 335 WESTLAKE CTR | DALY CITY | CA | 94015 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175900 | A5277 | 169 | 2375 RICHMOND AVE | STATEN ISLAND | NY | 10314 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175901 | A5290 | 811 | 1732 SUNRISE HWY | BAY SHORE | NY | 11706 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175904 | A5333 | 2051 | 138 W 34th ST | NEW YORK | NY | 10001 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175905 | A5326 | 933 | 7612 DENTON HWY | WATAUGA | TX | 76148 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175907 | A5325 | 1349 | 2909 FOREST LANE STE 100 | DALLAS | TX | 75234 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175909 | A5329 | 1864 | 9405 SAGE MEADOW TRAIL STE 101 | FORT WORTH | TX | 76177 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175910 | A5330 | 2095 | 1319 W STATE HWY 114, STE 300 | GRAPEVINE | TX | 76051 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175913 | A5324 | 160 | 209 W 125TH ST | NEW YORK | NY | 10027 |  | 2017-07-24 | [5 empty] | PILOT STORE
3183086 | A5358 | 6622 | 2660 11TH AVE | GREELEY | CO | 80631 |  | ASAP
3183089 | A5359 | 6623 | 3843 E 120TH ST | THORNTON | CO | 80233 |  | ASAP
3183789 | A5357 | 1903 | 435 WESTFARMS MALL | FARMINGTON | CT | 6032 |  | ASAP
3183785 | A5265 | 2173 | 6030 MARSHA SHARP FWY BLDG J STE 100 | LUBBOCK | TX | 79407 |  | ASAP
3183779 | A5375 | 6350 | 4650 TRANSMOUNTAIN DR #C | EL PASO | TX | 79924 |  | ASAP
3183784 | A5374 | 6354 | 1443 LEE TREVINO DR | EL PASO | TX | 79936 |  | ASAP
3183787 | A5282 | 7218 | 125 DOLSON AVE | MIDDLETOWN | NY | 10940 |  | ASAP
3183790 | A5356 | 7272 | 63 OVERLOOK TERRACE | HARTFORD | CT | 6106 |  | ASAP
3183791 | A5361 | 7278 | 196 E MAIN ST | NEW BRITAIN | CT | 6051 |  | ASAP
3183792 | A5360 | 7663 | 172 DANBURY RD | NEW MILFORD | CT | 6776 |  | ASAP
3183786 | A5273 | 7848 | 901 N GRANDVIEW | ODESSA | TX | 79761 |  | ASAP
3183801 | A5355 | 6426 | 339 SQUIRE RD | REVERE | MA | 2151 |  | ASAP |  |  |  |  | 7/31 - store remodeling. Royal unable to get into store to install DSDS. 8/3 - On hold indefinitely per Matt w/ Royal/ak
3183803 | A5369 | 6440 | 178 ALE WIFE BROOK PKWY | CAMBRIDGE | MA | 2138 |  | ASAP
3183797 | A5354 | 6441 | 164 EVERETT AVE | CHELSEA | MA | 2150 |  | ASAP
3183793 | A5281 | 7845 | 2910 N FIRST ST | ABILENE | TX | 79603 |  | ASAP
3183804 | A5368 | 6450 | 1615 BLUE HILL AVE | Mattapan | MA | 2126 |  | ASAP
3183806 | A5269 | 6461 | 110 PROVIDENCE HWY STE 1E | E WALPOLE | MA | 2032 |  | ASAP
3183795 |  | 7627 | 300 S BIBB STE F | EAGLE PASS | TX | 78852 |  | ASAP
3183808 |  | 7628 | 2730 S BRAHMA BLVD #120 | KINGSVILLE | TX | 78363 |  | ASAP
3183810 | A5373 | 418 | 255 E BASSE RD STE 1524 | SAN ANTONIO | TX | 78209 |  | 2017-07-31
3183811 | A5264 | 1303 | 7110 FM 78 STE 102 | SAN ANTONIO | TX | 78244 |  | 2017-07-31
3183812 | A5366 | 1314 | 9410 STATE HWY 151 STE 105 | SAN ANTONIO | TX | 78251 |  | 2017-07-31
3183814 | A5372 | 1388 | 3006 BROADWAY ST | SAN ANTONIO | TX | 78209 |  | 2017-07-31
3183815 | A5367 | 7533 | 310 VALLEY HI DR #302 | SAN ANTONIO | TX | 78227 |  | 2017-07-31
|  | 305 | 1701 MALLORY LN STE 150 | BRENTWOOD | TN | 37027 |  | 2017-08-03
3183877 | A5365 | 1876 | 1810 FM 685 STE 100 | PFLUGERVILLE | TX | 78660 |  | 2017-08-01
3183879 | A5364 | 2188 | 1000 E 41ST ST STE 840 | AUSTIN | TX | 78751 |  | 2017-08-01
3183880 | A5287 | 6398 | 2601 S IH 35 | ROUND ROCK | TX | 78664 |  | 2017-08-01
3183882 | A5288 | 6404 | 4301 W WILLIAM CANNON DR | AUSTIN | TX | 78745 |  | 2017-08-01
3183859 | A5342 | 6597 | 1765 SNOW RD | PARMA | OH | 44134 |  | 2017-08-01
3183860 | A5343 | 6598 | 22318 LAKE SHORE BLVD | EUCLID | OH | 44123 |  | 2017-08-01
3183862 | A5351 | 6599 | 3756 ROCKY RIVER RD | CLEVELAND | OH | 44111 |  | 2017-08-01
3183871 | A5350 | 6603 | 3551 BELMONT AVE | YOUNGSTOWN | OH | 44505 |  | 2017-08-01
3183872 | A5353 | 6610 | 1222 30TH ST NW | CANTON | OH | 44709 |  | 2017-08-01
3183873 | A5352 | 6613 | 1400 S ARLINGTON ST #164 | AKRON | OH | 44306 |  | 2017-08-01
|  | 7154 | 3983 NOLENSVILLE RD | NASHVILLE | TN | 37211 |  | 2017-08-03
|  | 7428 | 3833 E THOMAS RD STE A1 | PHOENIX | AZ | 85018 |  | 2017-08-03
3183875 | A5348 | 7439 | 100 FIFTH AVE | PITTSBURGH | PA | 15222 |  | 2017-08-01
3183876 | A5349 | 7444 | 3139 BANKSVILLE RD | PITTSBURGH | PA | 15216 |  | 2017-08-01
|  | 7705 | 1840 W VALENCIA | TUCSON | AZ | 85746 |  | 2017-08-03
|  | 7707 | 2071 E IRVINGTON RD | TUCSON | AZ | 85714 |  | 2017-08-03
|  | 7814 | 796 EASTERN PKWY | LOUISVILLE | KY | 40217 |  | 2017-08-03
3183883 | A5317 | 8389 | 1820 CRYSTAL FALLS PKWY STE 310 | LEANDER | TX | 78641 |  | 2017-08-01
3183891 | A5309 | 437 | 1310 W PIPELINE RD STE A4 | HURST | TX | 76053 |  | 2017-08-02
3183912 | A5347 | 1305 | 9464 ELLERBE RD STE 140 | SHREVEPORT | LA | 71106 |  | 2017-08-02
3183897 | A5344 | 1309 | 2906 BRENTWOOD DR STE 200 | LUFKIN | TX | 75901 |  | 2017-08-02
3183913 | A5346 | 1367 | 1806 E END BLVD STE 1300 | MARSHALL | TX | 75670 |  | 2017-08-02
3183892 | A5310 | 2181 | 6751 N MACARTHUR BLVD STE 150 | IRVING | TX | 75039 |  | 2017-08-02
|  | 6588 | 6611 GLENWAY AVE | CINCINNATI | OH | 45211 |  | 2017-08-03
3183893 | A5314 | 6672 | 1453 N SAGINAW STE 100 | SAGINAW | TX | 76179 |  | 2017-08-02
|  | 6700 | 524 W NEW CIRCLE RD #100 | LEXINGTON | KY | 40511 |  | 2017-08-03
|  | 6702 | 1301 WINCHESTER RD #69 | LEXINGTON | KY | 40505 |  | 2017-08-03
|  | 6939 | 7291 S EASTERN AVE | LAS VEGAS | NV | 89119 |  | 2017-08-03
|  | 8451 | 7325 S RAINBOW BLVD STE 120 | LAS VEGAS | NV | 89139 |  | 2017-08-03
|  | 8452 | 1980 S RAINBOW BLVD STE C100 | LAS VEGAS | NV | 89139 |  | 2017-08-03
3183889 | A5363 | 6414 | 1716 LIBERTY RD STE 4 | ELDERSBURG | MD | 21784 |  | 2017-08-03
3183890 | A5362 | 6420 | 559 RITCHIE HWY | SEVERNA PARK | MD | 21146 |  | 2017-08-03
|  | 6596 | 2132 E DOROTHY LN | KETTERING | OH | 45420 |  | 2017-08-03
3183908 | A5371 | 6655 | 803 GOVERNOR PLACE | BEAR | DE | 19701 |  | 2017-08-03
3183909 | A5370 | 6660 | 710 PEOPLES PLAZA | NEWARK | DE | 19702 |  | 2017-08-03
|  | 6814 | 8311 E WASHINGTON ST | INDIANAPOLIS | IN | 46219 |  | 2017-08-03
|  | 6821 | 2488 E WABASH ST | FRANKFORT | IN | 46041 |  | 2017-08-03
3183910 | A5319 | 7403 | 101 E OLNEY AVE | PHILADELPHIA | PA | 19120 |  | 2017-08-03
|  | 7492 | 1630 E 4TH ST STE J | ONTARIO | CA | 91764 |  | 2017-08-03
|  | 7495 | 23887 SUNNYMEAD BLVD #E | MORENO VALLEY | CA | 92553 |  | 2017-08-03
|  | 7499 | 17171 FOOTHILL BLVD # A | FONTANA | CA | 92335 |  | 2017-08-03
|  | 7501 | 50223 HARRISON ST STE B | COACHELLA | CA | 92236 |  | 2017-08-03
|  | 292 | 1881 N COBB PKWY | KENNESAW | GA | 30152 |  | 2017-08-05
|  | 891 | 266 S STRATFORD RD STE 24B | WINSTON SALEM | NC | 27103 |  | 2017-08-05
|  | 974 | 1208 BROADWAY STE 102 | CHULA VISTA | CA | 91911 |  | 2017-08-04
|  | 6371 | 65 LAWRENCEVILLE SUWANEE STE 14 | LAWRENCEVILLE | GA | 30044 |  | 2017-08-05
|  | 6379 | 102 W C BRYANT PKWY | CALHOUN | GA | 30701 |  | 2017-08-05
|  | 6384 | 6135 PEACHTREE PKWY #104 | NORCROSS | GA | 30092 |  | 2017-08-05
|  | 6582 | 140 S TUTTLE RD | SPRINGFIELD | OH | 45505 |  | 2017-08-04
|  | 6640 | 3760 E BROAD ST | COLUMBUS | OH | 43213 |  | 2017-08-04
|  | 6646 | 175 CENTRAL PKWY | HEATH | OH | 43056 |  | 2017-08-04
|  | 6878 | 10927 ATLANTIC AVE | LYNWOOD | CA | 90262 |  | 2017-08-04
|  | 7247 | 3742 VIRGINIA BCH BLV #F2 | VIRGINIA BEACH | VA | 23452 |  | 2017-08-05
|  | 7333 | 1478 N KRAEMER BLVD | PLACENTIA | CA | 92870 |  | 2017-08-04
|  | 7887 | 640 S VAN BUREN RD | EDEN | NC | 27288 |  | 2017-08-05
|  | 7891 | 1338 MEBANE OAKS RD | MEBANE | NC | 27302 |  | 2017-08-05
|  | 1218 | 1514 N WEST AVE | JACKSON | MI | 49202 |  | 2017-08-05
3183898 | A5345 | 1300 | 24926 FARM TO MARKET 1093 RD STE B | KATY | TX | 77494 |  | 2017-08-05
3183899 | A5312 | 1317 | 9630 WESTHEIMER RD STE 100 | HOUSTON | TX | 77063 |  | 2017-08-05
3183901 | A5340 | 2182 | 7459 SOUTHWEST FWY STE 200 | HOUSTON | TX | 77074 |  | 2017-08-05
|  | 6601 | 1222 OAK HARBOR RD | FREMONT | OH | 43420 |  | 2017-08-05
3183903 | A5341 | 6775 | 9001 SPENCER HWY #F | LAPORTE | TX | 77571 |  | 2017-08-05
3183904 | A5340 | 6778 | 5185 W 34TH ST STE 300 | HOUSTON | TX | 77092 |  | 2017-08-05
3183905 | A5313 | 6782 | 3533 PALMER HWY | TEXAS CITY | TX | 77590 |  | 2017-08-05
3183907 | A5308 | 6784 | 6888 GULF FRWY STE 630 | HOUSTON | TX | 77087 |  | 2017-08-05
|  | 6875 | 12730 HAWTHORNE BLVD #G | HAWTHORNE | CA | 90250 |  | 2017-08-05
|  | 6884 | 1714 S WESTERN AVE | LOS ANGELES | CA | 90006 |  | 2017-08-05
|  | 6893 | 482 E WASHINGTON BLVD | LOS ANGELES | CA | 90015 |  | 2017-08-05
|  | 6911 | 12980 FOOTHILL BLVD #G SP1 | SYLMAR | CA | 91342 |  | 2017-08-05
|  | 7702 | 821 W ALEXIS RD | TOLEDO | OH | 43612 |  | 2017-08-05
|  | 5539 | 4044 ALPINE NW | COMSTOCK PARK | MI | 49321 |  | 2017-08-06
|  | 6718 | 4073 N EUCLID AVE | BAY CITY | MI | 48706 |  | 2017-08-06
3184340 |  | 6990 | 250 CITIES SERVICE HWY | SULPHUR | LA | 70663 |  | 2017-08-06
|  | 7257 | 1512 N H ST STE E | LOMPOC | CA | 93436 |  | 2017-08-06
|  | 7612 | 280 E 10TH ST STE D | GILROY | CA | 95020 |  | 2017-08-06
|  | 7826 | 401 N CLIPPERT ST | LANSING | MI | 48912 |  | 2017-08-06
3184233 |  | 1342 | 5953 W PARK AVE STE 1029 | HOUMA | LA | 70364 |  | 2017-08-07
|  | 6542 | 1810 W 165TH ST | HAMMOND | IN | 46320 |  | 2017-08-07
|  | 6575 | 3150 S ASHLAND AVE | CHICAGO | IL | 60608 |  | 2017-08-07
3184236 | A5336 | 7178 | 717 CANAL ST | NEW ORLEANS | LA | 70130 |  | 2017-08-07
3184570 | A5253 | 7190 | 1595 GAUSE BLVD | SLIDELL | LA | 70458 |  | 2017-08-07
|  | 7192 | 216 N AIRLINE HWY | GONZALES | LA | 70737 |  | 2017-08-07
|  | 7561 | 3325 SONOMA BLVD STE 10 | VALLEJO | CA | 94590 |  | 2017-08-07
|  | 7564 | 2200 MACARTHUR BLVD #2200 | OAKLAND | CA | 94602 |  | 2017-08-07
|  | 7586 | 740 STONY POINT RD # B100 | SANTA ROSA | CA | 95401 |  | 2017-08-07
|  | 7972 | 420 BALDWIN ST | JENISON | MI | 49428 |  | 2017-08-07
|  | 1840 | 314 S UNIVERSITY STE 130 | LITTLE ROCK | AR | 72205 |  | 2017-08-08
|  | 2047 | 2602 KETTLEMAN LANE STE 130 | LODI | CA | 95242 |  | 2017-08-08
|  | 2160 | 1624 N MILWAUKEE AVE | CHICAGO | IL | 60647 |  | 2017-08-08
|  | 6547 | 2509 W CERMACK RD | CHICAGO | IL | 60608 |  | 2017-08-08
|  | 7098 | 1823A E GENEVA ST | DELAVAN | WI | 53115 |  | 2017-08-08
|  | 7568 | 644 BAILEY RD | PITTSBURG | CA | 94565 |  | 2017-08-08
|  | 7589 | 4498 LONE TREE WAY | ANTIOCH | CA | 94531 |  | 2017-08-08
3184328 |  | 2232 | 11637 OLIVE BLVD | SAINT LOUIS | MO | 63141 |  | 2017-08-09
|  | 6486 | 415 CLEVELAND ST | MUSCATINE | IA | 52761 |  | 2017-08-09
|  | 6698 | 1654 SYCAMORE ST | IOWA CITY | IA | 52240 |  | 2017-08-09
|  | 7102 | 3040 FISH HATCHERY RD | MADISON | WI | 53713 |  | 2017-08-09
3184337 |  | 7128 | 8218 N LINDBERGH BLVD | FLORISSANT | MO | 63031 |  | 2017-08-09
3184288 |  | 7135 | 5791 BELLEVILLE CROSSING | BELLEVILLE | IL | 62226 |  | 2017-08-09
|  | 7718 | 495 KEYSTONE AVE STE A | RENO | NV | 89503 |  | 2017-08-09
|  | 7109 | 109 WILLOW BEND | CRYSTAL | MN | 55428 |  | 2017-08-10
|  | 7114 | 3009 NICOLLET AVE | MINNEAPOLIS | MN | 55408 |  | 2017-08-10
|  | 7119 | 2868 S 26TH AVE | MINNEAPOLIS | MN | 55406 |  | 2017-08-10
|  | 7131 | 1824 S GLENSTONE | SPRINGFIELD | MO | 65804 |  | 2017-08-10
3184227 |  | 1186 | 1301 BALD HILL RD | WARWICK | RI | 2886 |  | 2017-08-11
3184228 |  | 2003 | 400 PUTNAM PIKE STE B2 | SMITHFIELD | RI | 2917 |  | 2017-08-11
|  | 6432 | 1375 LIBERTY ST | SPRINGFIELD | MA | 1104 |  | 2017-08-11
3184112 |  | 6435 | 68 STAFFORD ST | WORCESTER | MA | 1603 |  | 2017-08-11
3184223 |  | 6437 | 500 ROUTE 134 BLDG 1 | SOUTH DENNIS | MA | 2660 |  | 2017-08-11
3184225 |  | 6438 | 270 NEW STATE HWY UNIT #4 | RAYNHAM | MA | 2767 |  | 2017-08-11
3184214 |  | 6459 | 97 CHURCH ST | LOWELL | MA | 1852 |  | 2017-08-11
|  | 6499 | 4131 UNIVERSITY AVE | DES MOINES | IA | 50311 |  | 2017-08-11
|  | 7351 | 1480 NE BURNSIDE | GRESHAM | OR | 97030 |  | 2017-08-11
|  | 7367 | 18428 E BURNSIDE ST | PORTLAND | OR | 97233 |  | 2017-08-11
3184229 |  | 7473 | 232 GARFIELD AVE | CRANSTON | RI | 2920 |  | 2017-08-11
|  | 7804 | 3002 DODGE ST | OMAHA | NE | 68131 |  | 2017-08-11
3184257 |  | 7312 | 2127 NW 23RD ST | OKLAHOMA CITY | OK | 73107 |  | 2017-08-12
3184268 |  | 7321 | 711 N PERKINS RD | STILLWATER | OK | 74075 |  | 2017-08-12
|  | 7853 | 3820 RAINIER AVE S STE F | SEATTLE | WA | 98118 |  | 2017-08-12
|  | 7859 | 14902 PACIFIC AVE S | TACOMA | WA | 98444 |  | 2017-08-12
|  | 7864 | 2600 SW BARTON STE B-11 | SEATTLE | WA | 98126 |  | 2017-08-12
|  | 2186 | 15229 W 135TH ST | OLATHE | KS | 66062 |  | 2017-08-13
|  | 6829 | 1820 YAKIMA VALLEY HWY SPC A | SUNNYSIDE | WA | 98944 |  | 2017-08-13
|  | 6855 | 4365 NE CHOUTEAU TRFY #C | KANSAS CITY | MO | 64117 |  | 2017-08-13
|  | 6857 | 8312 E 171ST ST | BELTON | MO | 64012 |  | 2017-08-13
|  | 6865 | 105 SE STATE RTE 291 | LEES SUMMIT | MO | 64063 |  | 2017-08-13
|  | 6869 | 6236 N CHATHAM AVE | KANSAS CITY | MO | 64151 |  | 2017-08-13
|  | 6808 | 2922 E CLEVELAND BLVD | CALDWELL | ID | 83605 |  | 2017-08-14
|  | 507 | 1587 S STATE ST | OREM | UT | 84097 |  | 2017-08-15
|  | 171 | 275 ROUTE 46 WEST | TOTOWA | NJ | 7512 |  | 2017-08-03
|  | 181 | 2302 PALISADES CTR DR STE A202 | WEST NYACK | NY | 10994 |  | 2017-08-03
|  | 298 | 1899-1 N CONGRESS AVE | BOYNTON BEACH | FL | 33426 |  | 2017-08-03
|  | 697 | 2264 N MONROE ST STE 2 | TALLAHASSEE | FL | 32303 |  | 2017-08-03
|  | 704 | 2130 STATE ROUTE 35 | HOLMDEL | NJ | 7733 |  | 2017-08-03
|  | 1755 | 1 CROSSGATES MALL RD 207 | ALBANY | NY | 12203 |  | 2017-08-03
|  | 1850 | 1633 WP BALL BLVD | SANFORD | FL | 32771 |  | 2017-08-03
|  | 2077 | 3021 E COLONIAL DR | ORLANDO | FL | 32803 |  | 2017-08-03
|  | 2189 | 7332 W COLONIAL DR STE B | ORLANDO | FL | 32818 |  | 2017-08-03
|  | 4525 | 10300 W FOREST HILL BLVD | WELLINGTON | FL | 33414 |  | 2017-08-03
|  | 6506 | 67 S MAIN ST | NEPTUNE | NJ | 7753 |  | 2017-08-03
|  | 6752 | 400 N NAVY BLVD #B | PENSACOLA | FL | 32507 |  | 2017-08-03
|  | 6754 | 4610 MOBILE HWY #B | PENSACOLA | FL | 32506 |  | 2017-08-03
|  | 6838 | 2 NW 16TH AVE | GAINESVILLE | FL | 32601 |  | 2017-08-03
|  | 6839 | 3655 UNIVERSITY BLV W STE 1 | JACKSONVILLE | FL | 32217 |  | 2017-08-03
|  | 6840 | 4419 ROOSEVELT BLVD | JACKSONVILLE | FL | 32210 |  | 2017-08-03
|  | 6954 | 3491 HEMPSTEAD TURNPIKE | LEVITTOWN | NY | 11756 |  | 2017-08-03
|  | 6960 | 1530 UNION TURNPIKE | NEW HYDE PARK | NY | 11042 |  | 2017-08-03
|  | 6962 | 3554 LONG BEACH RD | OCEANSIDE | NY | 11572 |  | 2017-08-03
|  | 6964 | 385 S OYSTER BAY RD | PLAINVIEW | NY | 11803 |  | 2017-08-03
|  | 7068 | 6609 TAFT ST | HOLLYWOOD | FL | 33024 |  | 2017-08-03
|  | 7071 | 1780 STIRLING RD #103 | DANIA BEACH | FL | 33004 |  | 2017-08-03
|  | 7072 | 5411 N UNIVERSITY DR | LAUDERHILL | FL | 33351 |  | 2017-08-03
|  | 7073 | 75 E INDIANTOWN RD #605 | JUPITER | FL | 33477 |  | 2017-08-03
|  | 7074 | 5920 NW 183RD ST | MIAMI | FL | 33015 |  | 2017-08-03
|  | 7075 | 4246 NORTHLAKE BLVD | PALM BEACH GRDN | FL | 33410 |  | 2017-08-03
|  | 7090 | 13722 SW 56TH ST | MIAMI | FL | 33175 |  | 2017-08-03
|  | 7091 | 2520 SW 22ND ST | MIAMI | FL | 33145 |  | 2017-08-03
|  | 7204 | 1213 E 233RD ST | BRONX | NY | 10466 |  | 2017-08-03
|  | 7207 | 1351 FOREST AVE | STATEN ISLAND | NY | 10302 |  | 2017-08-03
|  | 7208 | 925 LEXINGTON AVE | NEW YORK | NY | 10021 |  | 2017-08-03
|  | 7212 | 134-40 SPRINGFIELD BLVD | SPRINGFIELD GDN | NY | 11413 |  | 2017-08-03
|  | 7217 | 144 E 98TH ST | BROOKLYN | NY | 11212 |  | 2017-08-03
|  | 7226 | 5119 5TH AVE | BROOKLYN | NY | 11220 |  | 2017-08-03
|  | 7283 | 135 BLOOMFIELD AVE | BLOOMFIELD | NJ | 7003 |  | 2017-08-03
|  | 7377 | 222 NORTH NOVA RD | ORMOND BEACH | FL | 32174 |  | 2017-08-03
|  | 7379 | 715 N 14TH ST | LEESBURG | FL | 34748 |  | 2017-08-03
|  | 7380 | 285 E VAN FLEET DR | BARTOW | FL | 33830 |  | 2017-08-03
|  | 7387 | 2036 US HWY 92 WEST | AUBURNDALE | FL | 33823 |  | 2017-08-03
|  | 7521 | 2833 W RIDGE RD STE 5 | ROCHESTER | NY | 14626 |  | 2017-08-03
|  | 7648 | 2310 S TAMIAMI TRL #1101 | PUNTA GORDA | FL | 33950 |  | 2017-08-03
|  | 7650 | 106 HANCOCK BRDG PKWY W STE A6 | CAPE CORAL | FL | 33991 |  | 2017-08-03
|  | 7658 | 2071 BLACK ROCK TPKE | FAIRFIELD | CT | 6825 |  | 2017-08-03
|  | 7676 | 259 NEW RD | SOMERS POINT | NJ | 8244 |  | 2017-08-03
|  | 7688 | 4933 34TH ST S | ST PETERSBURG | FL | 33711 |  | 2017-08-03
|  | 7690 | 8795 N 56TH ST | TEMPLE TERRACE | FL | 33617 |  | 2017-08-03
|  | 7997 | 969 STATE RD 434 West 434 CTR | LONGWOOD | FL | 32750 |  | 2017-08-03
|  | 8376 | 1701 SUNRISE HWY SP A15 | BAY SHORE | NY | 11706 |  | 2017-08-03

## DSDS Installs
Tracking # | CTI Asset # | Store# | Store address | City | State | Zip | Sprint Asset | Delivery date to store | 100% Complete (connected/confirmed) | Confirmed/Delivered not connected | Connected, location not confirmed (no call) | Shipped, not yet delivered to store/installed | Go back with Royal for network/missed rollout/damaged
3175895 | A5332 | 1841 | 3020 EL CERRITO PLAZA | EL CERRITO | CA | 94530 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175898 | A5328 | 1860 | 690 MARKET ST | SAN FRANCISCO | CA | 94104 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175899 | A5327 | 2009 | 335 WESTLAKE CTR | DALY CITY | CA | 94015 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175900 | A5277 | 169 | 2375 RICHMOND AVE | STATEN ISLAND | NY | 10314 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175901 | A5290 | 811 | 1732 SUNRISE HWY | BAY SHORE | NY | 11706 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175904 | A5333 | 2051 | 138 W 34th ST | NEW YORK | NY | 10001 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175905 | A5326 | 933 | 7612 DENTON HWY | WATAUGA | TX | 76148 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175907 | A5325 | 1349 | 2909 FOREST LANE STE 100 | DALLAS | TX | 75234 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175909 | A5329 | 1864 | 9405 SAGE MEADOW TRAIL STE 101 | FORT WORTH | TX | 76177 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175910 | A5330 | 2095 | 1319 W STATE HWY 114, STE 300 | GRAPEVINE | TX | 76051 |  | 2017-07-24 | [5 empty] | PILOT STORE
3175913 | A5324 | 160 | 209 W 125TH ST | NEW YORK | NY | 10027 |  | 2017-07-24 | [5 empty] | PILOT STORE
3183086 | A5358 | 6622 | 2660 11TH AVE | GREELEY | CO | 80631 |  | ASAP
3183089 | A5359 | 6623 | 3843 E 120TH ST | THORNTON | CO | 80233 |  | ASAP
3183789 | A5357 | 1903 | 435 WESTFARMS MALL | FARMINGTON | CT | 6032 |  | ASAP
3183785 | A5265 | 2173 | 6030 MARSHA SHARP FWY BLDG J STE 100 | LUBBOCK | TX | 79407 |  | ASAP
3183779 | A5375 | 6350 | 4650 TRANSMOUNTAIN DR #C | EL PASO | TX | 79924 |  | ASAP
3183784 | A5374 | 6354 | 1443 LEE TREVINO DR | EL PASO | TX | 79936 |  | ASAP
3183787 | A5282 | 7218 | 125 DOLSON AVE | MIDDLETOWN | NY | 10940 |  | ASAP
3183790 | A5356 | 7272 | 63 OVERLOOK TERRACE | HARTFORD | CT | 6106 |  | ASAP
3183791 | A5361 | 7278 | 196 E MAIN ST | NEW BRITAIN | CT | 6051 |  | ASAP
3183792 | A5360 | 7663 | 172 DANBURY RD | NEW MILFORD | CT | 6776 |  | ASAP
3183786 | A5273 | 7848 | 901 N GRANDVIEW | ODESSA | TX | 79761 |  | ASAP
3183801 | A5355 | 6426 | 339 SQUIRE RD | REVERE | MA | 2151 |  | ASAP |  |  |  |  | 7/31 - store remodeling. Royal unable to get into store to install DSDS.
3183803 | A5369 | 6440 | 178 ALE WIFE BROOK PKWY | CAMBRIDGE | MA | 2138 |  | ASAP
3183797 | A5354 | 6441 | 164 EVERETT AVE | CHELSEA | MA | 2150 |  | ASAP
3183793 | A5281 | 7845 | 2910 N FIRST ST | ABILENE | TX | 79603 |  | ASAP
3183804 | A5368 | 6450 | 1615 BLUE HILL AVE | Mattapan | MA | 2126 |  | ASAP
3183806 | A5269 | 6461 | 110 PROVIDENCE HWY STE 1E | E WALPOLE | MA | 2032 |  | ASAP
3183795 |  | 7627 | 300 S BIBB STE F | EAGLE PASS | TX | 78852 |  | ASAP
3183808 |  | 7628 | 2730 S BRAHMA BLVD #120 | KINGSVILLE | TX | 78363 |  | ASAP
3183810 | A5373 | 418 | 255 E BASSE RD STE 1524 | SAN ANTONIO | TX | 78209 |  | 2017-07-31
3183811 | A5264 | 1303 | 7110 FM 78 STE 102 | SAN ANTONIO | TX | 78244 |  | 2017-07-31
3183812 | A5366 | 1314 | 9410 STATE HWY 151 STE 105 | SAN ANTONIO | TX | 78251 |  | 2017-07-31
3183814 | A5372 | 1388 | 3006 BROADWAY ST | SAN ANTONIO | TX | 78209 |  | 2017-07-31
3183815 | A5367 | 7533 | 310 VALLEY HI DR #302 | SAN ANTONIO | TX | 78227 |  | 2017-07-31
|  | 305 | 1701 MALLORY LN STE 150 | BRENTWOOD | TN | 37027 |  | 2017-08-03
3183877 | A5365 | 1876 | 1810 FM 685 STE 100 | PFLUGERVILLE | TX | 78660 |  | 2017-08-01
3183879 | A5364 | 2188 | 1000 E 41ST ST STE 840 | AUSTIN | TX | 78751 |  | 2017-08-01
3183880 | A5287 | 6398 | 2601 S IH 35 | ROUND ROCK | TX | 78664 |  | 2017-08-01
3183882 | A5288 | 6404 | 4301 W WILLIAM CANNON DR | AUSTIN | TX | 78745 |  | 2017-08-01
3183859 | A5342 | 6597 | 1765 SNOW RD | PARMA | OH | 44134 |  | 2017-08-01
3183860 | A5343 | 6598 | 22318 LAKE SHORE BLVD | EUCLID | OH | 44123 |  | 2017-08-01
3183862 | A5351 | 6599 | 3756 ROCKY RIVER RD | CLEVELAND | OH | 44111 |  | 2017-08-01
3183871 | A5350 | 6603 | 3551 BELMONT AVE | YOUNGSTOWN | OH | 44505 |  | 2017-08-01
3183872 | A5353 | 6610 | 1222 30TH ST NW | CANTON | OH | 44709 |  | 2017-08-01
3183873 | A5352 | 6613 | 1400 S ARLINGTON ST #164 | AKRON | OH | 44306 |  | 2017-08-01
|  | 7154 | 3983 NOLENSVILLE RD | NASHVILLE | TN | 37211 |  | 2017-08-03
|  | 7428 | 3833 E THOMAS RD STE A1 | PHOENIX | AZ | 85018 |  | 2017-08-03
3183875 | A5348 | 7439 | 100 FIFTH AVE | PITTSBURGH | PA | 15222 |  | 2017-08-01
3183876 | A5349 | 7444 | 3139 BANKSVILLE RD | PITTSBURGH | PA | 15216 |  | 2017-08-01
|  | 7705 | 1840 W VALENCIA | TUCSON | AZ | 85746 |  | 2017-08-03
|  | 7707 | 2071 E IRVINGTON RD | TUCSON | AZ | 85714 |  | 2017-08-03
|  | 7814 | 796 EASTERN PKWY | LOUISVILLE | KY | 40217 |  | 2017-08-03
3183883 | A5317 | 8389 | 1820 CRYSTAL FALLS PKWY STE 310 | LEANDER | TX | 78641 |  | 2017-08-01
3183891 | A5309 | 437 | 1310 W PIPELINE RD STE A4 | HURST | TX | 76053 |  | 2017-08-02
3183912 | A5347 | 1305 | 9464 ELLERBE RD STE 140 | SHREVEPORT | LA | 71106 |  | 2017-08-02
3183897 | A5344 | 1309 | 2906 BRENTWOOD DR STE 200 | LUFKIN | TX | 75901 |  | 2017-08-02
3183913 | A5346 | 1367 | 1806 E END BLVD STE 1300 | MARSHALL | TX | 75670 |  | 2017-08-02
3183892 | A5310 | 2181 | 6751 N MACARTHUR BLVD STE 150 | IRVING | TX | 75039 |  | 2017-08-02
|  | 6588 | 6611 GLENWAY AVE | CINCINNATI | OH | 45211 |  | 2017-08-03
3183893 | A5314 | 6672 | 1453 N SAGINAW STE 100 | SAGINAW | TX | 76179 |  | 2017-08-02
|  | 6700 | 524 W NEW CIRCLE RD #100 | LEXINGTON | KY | 40511 |  | 2017-08-03
|  | 6702 | 1301 WINCHESTER RD #69 | LEXINGTON | KY | 40505 |  | 2017-08-03
|  | 6939 | 7291 S EASTERN AVE | LAS VEGAS | NV | 89119 |  | 2017-08-03
|  | 8451 | 7325 S RAINBOW BLVD STE 120 | LAS VEGAS | NV | 89139 |  | 2017-08-03
|  | 8452 | 1980 S RAINBOW BLVD STE C100 | LAS VEGAS | NV | 89139 |  | 2017-08-03
3183889 | A5363 | 6414 | 1716 LIBERTY RD STE 4 | ELDERSBURG | MD | 21784 |  | 2017-08-03
3183890 | A5362 | 6420 | 559 RITCHIE HWY | SEVERNA PARK | MD | 21146 |  | 2017-08-03
|  | 6596 | 2132 E DOROTHY LN | KETTERING | OH | 45420 |  | 2017-08-03
3183908 | A5371 | 6655 | 803 GOVERNOR PLACE | BEAR | DE | 19701 |  | 2017-08-03
3183909 | A5370 | 6660 | 710 PEOPLES PLAZA | NEWARK | DE | 19702 |  | 2017-08-03
|  | 6814 | 8311 E WASHINGTON ST | INDIANAPOLIS | IN | 46219 |  | 2017-08-03
|  | 6821 | 2488 E WABASH ST | FRANKFORT | IN | 46041 |  | 2017-08-03
3183910 | A5319 | 7403 | 101 E OLNEY AVE | PHILADELPHIA | PA | 19120 |  | 2017-08-03
|  | 7492 | 1630 E 4TH ST STE J | ONTARIO | CA | 91764 |  | 2017-08-03
|  | 7495 | 23887 SUNNYMEAD BLVD #E | MORENO VALLEY | CA | 92553 |  | 2017-08-03
|  | 7499 | 17171 FOOTHILL BLVD # A | FONTANA | CA | 92335 |  | 2017-08-03
|  | 7501 | 50223 HARRISON ST STE B | COACHELLA | CA | 92236 |  | 2017-08-03
|  | 292 | 1881 N COBB PKWY | KENNESAW | GA | 30152 |  | 2017-08-05
|  | 891 | 266 S STRATFORD RD STE 24B | WINSTON SALEM | NC | 27103 |  | 2017-08-05
|  | 974 | 1208 BROADWAY STE 102 | CHULA VISTA | CA | 91911 |  | 2017-08-04
|  | 6371 | 65 LAWRENCEVILLE SUWANEE STE 14 | LAWRENCEVILLE | GA | 30044 |  | 2017-08-05
|  | 6379 | 102 W C BRYANT PKWY | CALHOUN | GA | 30701 |  | 2017-08-05
|  | 6384 | 6135 PEACHTREE PKWY #104 | NORCROSS | GA | 30092 |  | 2017-08-05
|  | 6582 | 140 S TUTTLE RD | SPRINGFIELD | OH | 45505 |  | 2017-08-04
|  | 6640 | 3760 E BROAD ST | COLUMBUS | OH | 43213 |  | 2017-08-04
|  | 6646 | 175 CENTRAL PKWY | HEATH | OH | 43056 |  | 2017-08-04
|  | 6878 | 10927 ATLANTIC AVE | LYNWOOD | CA | 90262 |  | 2017-08-04
|  | 7247 | 3742 VIRGINIA BCH BLV #F2 | VIRGINIA BEACH | VA | 23452 |  | 2017-08-05
|  | 7333 | 1478 N KRAEMER BLVD | PLACENTIA | CA | 92870 |  | 2017-08-04
|  | 7887 | 640 S VAN BUREN RD | EDEN | NC | 27288 |  | 2017-08-05
|  | 7891 | 1338 MEBANE OAKS RD | MEBANE | NC | 27302 |  | 2017-08-05
|  | 1218 | 1514 N WEST AVE | JACKSON | MI | 49202 |  | 2017-08-05
3183898 | A5345 | 1300 | 24926 FARM TO MARKET 1093 RD STE B | KATY | TX | 77494 |  | 2017-08-05
3183899 | A5312 | 1317 | 9630 WESTHEIMER RD STE 100 | HOUSTON | TX | 77063 |  | 2017-08-05
3183901 | A5340 | 2182 | 7459 SOUTHWEST FWY STE 200 | HOUSTON | TX | 77074 |  | 2017-08-05
|  | 6601 | 1222 OAK HARBOR RD | FREMONT | OH | 43420 |  | 2017-08-05
3183903 | A5341 | 6775 | 9001 SPENCER HWY #F | LAPORTE | TX | 77571 |  | 2017-08-05
3183904 | A5340 | 6778 | 5185 W 34TH ST STE 300 | HOUSTON | TX | 77092 |  | 2017-08-05
3183905 | A5313 | 6782 | 3533 PALMER HWY | TEXAS CITY | TX | 77590 |  | 2017-08-05
3183907 | A5308 | 6784 | 6888 GULF FRWY STE 630 | HOUSTON | TX | 77087 |  | 2017-08-05
|  | 6875 | 12730 HAWTHORNE BLVD #G | HAWTHORNE | CA | 90250 |  | 2017-08-05
|  | 6884 | 1714 S WESTERN AVE | LOS ANGELES | CA | 90006 |  | 2017-08-05
|  | 6893 | 482 E WASHINGTON BLVD | LOS ANGELES | CA | 90015 |  | 2017-08-05
|  | 6911 | 12980 FOOTHILL BLVD #G SP1 | SYLMAR | CA | 91342 |  | 2017-08-05
|  | 7702 | 821 W ALEXIS RD | TOLEDO | OH | 43612 |  | 2017-08-05
|  | 5539 | 4044 ALPINE NW | COMSTOCK PARK | MI | 49321 |  | 2017-08-06
|  | 6718 | 4073 N EUCLID AVE | BAY CITY | MI | 48706 |  | 2017-08-06
3184340 |  | 6990 | 250 CITIES SERVICE HWY | SULPHUR | LA | 70663 |  | 2017-08-06
|  | 7257 | 1512 N H ST STE E | LOMPOC | CA | 93436 |  | 2017-08-06
|  | 7612 | 280 E 10TH ST STE D | GILROY | CA | 95020 |  | 2017-08-06
|  | 7826 | 401 N CLIPPERT ST | LANSING | MI | 48912 |  | 2017-08-06
3184233 |  | 1342 | 5953 W PARK AVE STE 1029 | HOUMA | LA | 70364 |  | 2017-08-07
|  | 6542 | 1810 W 165TH ST | HAMMOND | IN | 46320 |  | 2017-08-07
|  | 6575 | 3150 S ASHLAND AVE | CHICAGO | IL | 60608 |  | 2017-08-07
3184236 |  | 7178 | 717 CANAL ST | NEW ORLEANS | LA | 70130 |  | 2017-08-07
3184570 | A5253 | 7190 | 1595 GAUSE BLVD | SLIDELL | LA | 70458 |  | 2017-08-07
|  | 7192 | 216 N AIRLINE HWY | GONZALES | LA | 70737 |  | 2017-08-07
|  | 7561 | 3325 SONOMA BLVD STE 10 | VALLEJO | CA | 94590 |  | 2017-08-07
|  | 7564 | 2200 MACARTHUR BLVD #2200 | OAKLAND | CA | 94602 |  | 2017-08-07
|  | 7586 | 740 STONY POINT RD # B100 | SANTA ROSA | CA | 95401 |  | 2017-08-07
|  | 7972 | 420 BALDWIN ST | JENISON | MI | 49428 |  | 2017-08-07
|  | 1840 | 314 S UNIVERSITY STE 130 | LITTLE ROCK | AR | 72205 |  | 2017-08-08
|  | 2047 | 2602 KETTLEMAN LANE STE 130 | LODI | CA | 95242 |  | 2017-08-08
|  | 2160 | 1624 N MILWAUKEE AVE | CHICAGO | IL | 60647 |  | 2017-08-08
|  | 6547 | 2509 W CERMACK RD | CHICAGO | IL | 60608 |  | 2017-08-08
|  | 7098 | 1823A E GENEVA ST | DELAVAN | WI | 53115 |  | 2017-08-08
|  | 7568 | 644 BAILEY RD | PITTSBURG | CA | 94565 |  | 2017-08-08
|  | 7589 | 4498 LONE TREE WAY | ANTIOCH | CA | 94531 |  | 2017-08-08
3184328 |  | 2232 | 11637 OLIVE BLVD | SAINT LOUIS | MO | 63141 |  | 2017-08-09
|  | 6486 | 415 CLEVELAND ST | MUSCATINE | IA | 52761 |  | 2017-08-09
|  | 6698 | 1654 SYCAMORE ST | IOWA CITY | IA | 52240 |  | 2017-08-09
|  | 7102 | 3040 FISH HATCHERY RD | MADISON | WI | 53713 |  | 2017-08-09
3184337 |  | 7128 | 8218 N LINDBERGH BLVD | FLORISSANT | MO | 63031 |  | 2017-08-09
3184288 |  | 7135 | 5791 BELLEVILLE CROSSING | BELLEVILLE | IL | 62226 |  | 2017-08-09
|  | 7718 | 495 KEYSTONE AVE STE A | RENO | NV | 89503 |  | 2017-08-09
|  | 7109 | 109 WILLOW BEND | CRYSTAL | MN | 55428 |  | 2017-08-10
|  | 7114 | 3009 NICOLLET AVE | MINNEAPOLIS | MN | 55408 |  | 2017-08-10
|  | 7119 | 2868 S 26TH AVE | MINNEAPOLIS | MN | 55406 |  | 2017-08-10
|  | 7131 | 1824 S GLENSTONE | SPRINGFIELD | MO | 65804 |  | 2017-08-10
3184227 |  | 1186 | 1301 BALD HILL RD | WARWICK | RI | 2886 |  | 2017-08-11
3184228 |  | 2003 | 400 PUTNAM PIKE STE B2 | SMITHFIELD | RI | 2917 |  | 2017-08-11
|  | 6432 | 1375 LIBERTY ST | SPRINGFIELD | MA | 1104 |  | 2017-08-11
3184112 |  | 6435 | 68 STAFFORD ST | WORCESTER | MA | 1603 |  | 2017-08-11
3184223 |  | 6437 | 500 ROUTE 134 BLDG 1 | SOUTH DENNIS | MA | 2660 |  | 2017-08-11
3184225 |  | 6438 | 270 NEW STATE HWY UNIT #4 | RAYNHAM | MA | 2767 |  | 2017-08-11
3184214 |  | 6459 | 97 CHURCH ST | LOWELL | MA | 1852 |  | 2017-08-11
|  | 6499 | 4131 UNIVERSITY AVE | DES MOINES | IA | 50311 |  | 2017-08-11
|  | 7351 | 1480 NE BURNSIDE | GRESHAM | OR | 97030 |  | 2017-08-11
|  | 7367 | 18428 E BURNSIDE ST | PORTLAND | OR | 97233 |  | 2017-08-11
3184229 |  | 7473 | 232 GARFIELD AVE | CRANSTON | RI | 2920 |  | 2017-08-11
|  | 7804 | 3002 DODGE ST | OMAHA | NE | 68131 |  | 2017-08-11
3184257 |  | 7312 | 2127 NW 23RD ST | OKLAHOMA CITY | OK | 73107 |  | 2017-08-12
3184268 |  | 7321 | 711 N PERKINS RD | STILLWATER | OK | 74075 |  | 2017-08-12
|  | 7853 | 3820 RAINIER AVE S STE F | SEATTLE | WA | 98118 |  | 2017-08-12
|  | 7859 | 14902 PACIFIC AVE S | TACOMA | WA | 98444 |  | 2017-08-12
|  | 7864 | 2600 SW BARTON STE B-11 | SEATTLE | WA | 98126 |  | 2017-08-12
|  | 2186 | 15229 W 135TH ST | OLATHE | KS | 66062 |  | 2017-08-13
|  | 6829 | 1820 YAKIMA VALLEY HWY SPC A | SUNNYSIDE | WA | 98944 |  | 2017-08-13
|  | 6855 | 4365 NE CHOUTEAU TRFY #C | KANSAS CITY | MO | 64117 |  | 2017-08-13
|  | 6857 | 8312 E 171ST ST | BELTON | MO | 64012 |  | 2017-08-13
|  | 6865 | 105 SE STATE RTE 291 | LEES SUMMIT | MO | 64063 |  | 2017-08-13
|  | 6869 | 6236 N CHATHAM AVE | KANSAS CITY | MO | 64151 |  | 2017-08-13
|  | 6808 | 2922 E CLEVELAND BLVD | CALDWELL | ID | 83605 |  | 2017-08-14
|  | 507 | 1587 S STATE ST | OREM | UT | 84097 |  | 2017-08-15
|  | 171 | 275 ROUTE 46 WEST | TOTOWA | NJ | 7512 |  | 2017-08-03
|  | 181 | 2302 PALISADES CTR DR STE A202 | WEST NYACK | NY | 10994 |  | 2017-08-03
|  | 298 | 1899-1 N CONGRESS AVE | BOYNTON BEACH | FL | 33426 |  | 2017-08-03
|  | 697 | 2264 N MONROE ST STE 2 | TALLAHASSEE | FL | 32303 |  | 2017-08-03
|  | 704 | 2130 STATE ROUTE 35 | HOLMDEL | NJ | 7733 |  | 2017-08-03
|  | 1755 | 1 CROSSGATES MALL RD 207 | ALBANY | NY | 12203 |  | 2017-08-03
|  | 1850 | 1633 WP BALL BLVD | SANFORD | FL | 32771 |  | 2017-08-03
|  | 2077 | 3021 E COLONIAL DR | ORLANDO | FL | 32803 |  | 2017-08-03
|  | 2189 | 7332 W COLONIAL DR STE B | ORLANDO | FL | 32818 |  | 2017-08-03
|  | 4525 | 10300 W FOREST HILL BLVD | WELLINGTON | FL | 33414 |  | 2017-08-03
|  | 6506 | 67 S MAIN ST | NEPTUNE | NJ | 7753 |  | 2017-08-03
|  | 6752 | 400 N NAVY BLVD #B | PENSACOLA | FL | 32507 |  | 2017-08-03
|  | 6754 | 4610 MOBILE HWY #B | PENSACOLA | FL | 32506 |  | 2017-08-03
|  | 6838 | 2 NW 16TH AVE | GAINESVILLE | FL | 32601 |  | 2017-08-03
|  | 6839 | 3655 UNIVERSITY BLV W STE 1 | JACKSONVILLE | FL | 32217 |  | 2017-08-03
|  | 6840 | 4419 ROOSEVELT BLVD | JACKSONVILLE | FL | 32210 |  | 2017-08-03
|  | 6954 | 3491 HEMPSTEAD TURNPIKE | LEVITTOWN | NY | 11756 |  | 2017-08-03
|  | 6960 | 1530 UNION TURNPIKE | NEW HYDE PARK | NY | 11042 |  | 2017-08-03
|  | 6962 | 3554 LONG BEACH RD | OCEANSIDE | NY | 11572 |  | 2017-08-03
|  | 6964 | 385 S OYSTER BAY RD | PLAINVIEW | NY | 11803 |  | 2017-08-03
|  | 7068 | 6609 TAFT ST | HOLLYWOOD | FL | 33024 |  | 2017-08-03
|  | 7071 | 1780 STIRLING RD #103 | DANIA BEACH | FL | 33004 |  | 2017-08-03
|  | 7072 | 5411 N UNIVERSITY DR | LAUDERHILL | FL | 33351 |  | 2017-08-03
|  | 7073 | 75 E INDIANTOWN RD #605 | JUPITER | FL | 33477 |  | 2017-08-03
|  | 7074 | 5920 NW 183RD ST | MIAMI | FL | 33015 |  | 2017-08-03
|  | 7075 | 4246 NORTHLAKE BLVD | PALM BEACH GRDN | FL | 33410 |  | 2017-08-03
|  | 7090 | 13722 SW 56TH ST | MIAMI | FL | 33175 |  | 2017-08-03
|  | 7091 | 2520 SW 22ND ST | MIAMI | FL | 33145 |  | 2017-08-03
|  | 7204 | 1213 E 233RD ST | BRONX | NY | 10466 |  | 2017-08-03
|  | 7207 | 1351 FOREST AVE | STATEN ISLAND | NY | 10302 |  | 2017-08-03
|  | 7208 | 925 LEXINGTON AVE | NEW YORK | NY | 10021 |  | 2017-08-03
|  | 7212 | 134-40 SPRINGFIELD BLVD | SPRINGFIELD GDN | NY | 11413 |  | 2017-08-03
|  | 7217 | 144 E 98TH ST | BROOKLYN | NY | 11212 |  | 2017-08-03
|  | 7226 | 5119 5TH AVE | BROOKLYN | NY | 11220 |  | 2017-08-03
|  | 7283 | 135 BLOOMFIELD AVE | BLOOMFIELD | NJ | 7003 |  | 2017-08-03
|  | 7377 | 222 NORTH NOVA RD | ORMOND BEACH | FL | 32174 |  | 2017-08-03
|  | 7379 | 715 N 14TH ST | LEESBURG | FL | 34748 |  | 2017-08-03
|  | 7380 | 285 E VAN FLEET DR | BARTOW | FL | 33830 |  | 2017-08-03
|  | 7387 | 2036 US HWY 92 WEST | AUBURNDALE | FL | 33823 |  | 2017-08-03
|  | 7521 | 2833 W RIDGE RD STE 5 | ROCHESTER | NY | 14626 |  | 2017-08-03
|  | 7648 | 2310 S TAMIAMI TRL #1101 | PUNTA GORDA | FL | 33950 |  | 2017-08-03
|  | 7650 | 106 HANCOCK BRDG PKWY W STE A6 | CAPE CORAL | FL | 33991 |  | 2017-08-03
|  | 7658 | 2071 BLACK ROCK TPKE | FAIRFIELD | CT | 6825 |  | 2017-08-03
|  | 7676 | 259 NEW RD | SOMERS POINT | NJ | 8244 |  | 2017-08-03
|  | 7688 | 4933 34TH ST S | ST PETERSBURG | FL | 33711 |  | 2017-08-03
|  | 7690 | 8795 N 56TH ST | TEMPLE TERRACE | FL | 33617 |  | 2017-08-03
|  | 7997 | 969 STATE RD 434 West 434 CTR | LONGWOOD | FL | 32750 |  | 2017-08-03
|  | 8376 | 1701 SUNRISE HWY SP A15 | BAY SHORE | NY | 11706 |  | 2017-08-03